## IID-VDOT SGR Bridge Projects
VDOT-Owned SGR Bridge Project Selection
Final Draft Update to FY23-FY28 SYIP
Based on July 1, 2021 BrM data
Issued: 5/23/2022
BASIC STRUCTURAL INFORMATION | [6 empty] | PROJECT COST ESTIMATES AND SCHEDULES
FED ID | District | VDOT / Locality | Route No. | Facility Carried | Facility Intersected | Functional Classification | UPC / Temp. UPC (If Applicable) | Project Scope | BROS Eligibility | Total Project Cost Estimate | PE Phase Cost Estimate | RW Phase Cost Estimate | CN Phase Cost Estimate | District Schedule Priority | PE Phase Schedule (Start) | PE Phase Schedule (End) | RW Phase Schedule (Start) | RW Phase Schedule (End) | CN Phase Schedule (Start) | CN Phase Schedule (End) | Notes to IID
17426 | 1 - Bristol | VDOT | 81 | INTERSTATE 81 SBL | M. FORK HOLSTON RIVER | Rural Principal Arterial - Interstate | T26486 | Bridge Replacement | No | 15233342.5 | 962364.5 | 70523.5 | 14200454.5 | 1 | 2025-07-01 | 2027-07-01 | 2026-07-01 | 2027-07-01 | 2027-07-01 | 2030-10-01
17427 | 1 - Bristol | VDOT | 81 | INTERSTATE 81 NBL | M. FORK HOLSTON RIVER | Rural Principal Arterial - Interstate | T26486 | Bridge Replacement | No | 15233342.5 | 962364.5 | 70523.5 | 14200454.5 | 1 | 2025-07-01 | 2027-07-01 | 2026-07-01 | 2027-07-01 | 2027-07-01 | 2030-10-01
8730 | 1 - Bristol | VDOT | 58 | HIGHLANDS PKWY | CABIN CREEK | Rural Principal Arterial - Other | T26475 | Bridge Replacement | No | 4706119 | 791205 | 585086 | 3329828 | 2 | 2026-07-01 | 2027-07-01 | 2027-07-01 | 2028-07-01 | 2028-07-01 | 2029-12-01
19743 | 1 - Bristol | VDOT | 671 | CRIGGER ROAD | HARRIS BRANCH | Rural Local | T26489 | Bridge Replacement | Yes | 3910948.65 | 500149.98 | 202872.96 | 3207925.71 | 3 | 2026-07-01 | 2026-07-01 | 2027-07-01 | 2028-07-01 | 2028-07-01 | 2029-12-01
16438 | 1 - Bristol | VDOT | 634 | PINE CREEK ROAD | PINE CREEK | Rural Local | T26479 | Bridge Replacement | Yes | 4240644.34 | 616733.81 | 223884.81 | 3400025.72 | 4 | 2026-07-01 | 2027-07-01 | 2027-07-01 | 2028-07-01 | 2028-07-01 | 2029-12-01
19677 | 1 - Bristol | VDOT | 619 | GLEAVES ROAD | CRIPPLE CREEK | Rural Major Collector | T26487 | Bridge Replacement | No | 10757068 | 1448583 | 626877 | 8681608 | 5 | 2026-07-01 | 2026-07-01 | 2027-07-01 | 2028-07-01 | 2028-07-01 | 2029-12-01
16699 | 1 - Bristol | VDOT | 624 | FRALEYTOWN RD | N FORK CLINCH RIVER | Rural Local | T26482 | Bridge Replacement | Yes | 3579843 | 307718 | 179108 | 3093017 | 6 | 2026-07-01 | 2027-07-01 | 2027-07-01 | 2028-07-01 | 2028-07-01 | 2029-12-01
16806 | 1 - Bristol | VDOT | 669 | MINERAL HILL LANE | BIG MOCCASIN CREEK | Rural Local | T26485 | Bridge Replacement | Yes | 4563184.71 | 616733.81 | 268662 | 3677788.9 | 7 | 2026-07-01 | 2026-07-01 | 2027-07-01 | 2028-07-01 | 2028-07-01 | 2029-12-01
12292 | 2 - Salem | VDOT | 663 | Walton Road/663 | Crab Creek | Rural Major Collector | 117012 | Bridge Replacement | No | 9731817 | 1318459 | 756048 | 7657310 | 2 | 2026-07-01 | 2028-07-01 | 2028-07-01 | 2029-08-01 | 2029-08-01 | 2031-08-01
13897 | 3 - Lynchburg | VDOT | 360 | EBL Route 360 | Grade Crossing | Rural Principal Arterial - Other | T26504 | Bridge Replacement | No | 11131186 | 1372593 | 373534 | 9385059 | 1 | 2026-10-01 | 2026-10-01 | 2029-05-22 | 2030-05-14 | 2030-05-14 | 2032-02-24
13473 | 3 - Lynchburg | VDOT | 40 | Gretna Road | Pigg River | Rural Minor Arterial | T25139 | Bridge Replacement | No | 23354077 | 1831246 | 1448010 | 20074821 | 2 | 2026-10-01 | 2030-07-05 | 2030-07-05 | 2031-11-11 | 2031-11-11 | 2033-09-26
3552 | 4 - Richmond | VDOT | 1 | U.S. 1 (NBL) | SHINING CREEK | Rural Major Collector | T26692 | Bridge Replacement | No | 10467323 | 1675120 | 77503 | 8714700 | 1 | 2026-07-01 | 2026-07-01 | 2029-04-13 | 2030-01-09 | 2030-01-09 | 2031-07-22
11911 | 4 - Richmond | VDOT | 85 | SBL ROUTE I-85 | ROANOKE RIVER | Rural Principal Arterial - Interstate | T26701 | Bridge Rehabilitation - Deck Replacement | No | 27509528 | 3261560 | 0 | 24247968 | 2 | 2026-07-01 | 2030-02-12 | 2030-02-12 | 2031-05-12 | 2031-05-12 | 2033-12-22
5341 | 4 - Richmond | VDOT | 746 | ENON CHURCH ROAD | JOHNSON CREEK | Urban Minor Arterial | T26697 | Culvert Replacement | No | 5794950 | 1176810 | 532190 | 4085950 | 3 | 2026-07-01 | 2026-07-01 | 2029-04-15 | 2030-08-12 | 2030-08-12 | 2032-03-01
5272 | 4 - Richmond | VDOT | 637 | HOPKINS ROAD | FALLING CREEK | Urban Minor Arterial | T26694 | Bridge Replacement | No | 9902088 | 1635700 | 1195400 | 7070988 | 4 | 2025-07-01 | 2028-04-13 | 2028-04-13 | 2030-02-12 | 2030-02-12 | 2031-08-21
23260 | 4 - Richmond | VDOT | 724 | SPRUCE AVENUE | JOHNSON CREEK | Rural Local | T26703 | Culvert Replacement | Yes | 6386255 | 1176520 | 657274 | 4552461 | 5 | 2026-07-01 | 2029-04-02 | 2029-04-02 | 2030-08-12 | 2030-08-12 | 2033-02-13
11878 | 4 - Richmond | VDOT | 58 | U.S 58 BUSINESS | COLEMANS CREEK | Rural Major Collector | T26700 | Bridge Replacement | No | 7213604 | 1285630 | 578840 | 5349134 | 6 | 2025-07-01 | 2025-07-01 | 2028-03-31 | 2028-10-30 | 2029-09-27 | 2032-02-17
6064 | 4 - Richmond | VDOT | 639 | WILSON ROAD | NAMOZINE CREEK | Rural Local | T26698 | Bridge Replacement | Yes | 6463383 | 1176760 | 352890 | 4933733 | 7 | 2026-07-01 | 2029-04-13 | 2029-04-13 | 2030-08-14 | 2030-08-14 | 2032-03-03
5328 | 4 - Richmond | VDOT | 678 | WEST PROVIDENCE RD | BRANCH OF FALLING CREEK | Urban Minor Arterial | T26696 | Bridge Replacement | No | 10515177 | 1757860 | 867190 | 7890127 | 8 | 2026-07-01 | 2026-07-01 | 2029-04-13 | 2030-08-14 | 2030-08-14 | 2032-03-03
12704 | 4 - Richmond | VDOT | 106 | EMMAUS CHURCH ROAD | RTES I 64 & 33 | Rural Minor Arterial | T26702 | Superstructure Replacement | No | 31247230 | 3692220 | 0 | 27555010 | 9 | 2026-07-01 | 2030-02-12 | 2030-02-12 | 2031-05-12 | 2031-05-12 | 2033-12-22
4809 | 4 - Richmond | VDOT | 607 | WAYSIDE ROAD | WEST RUN | Rural Major Collector | T26693 | Bridge Replacement | No | 6324904 | 1176090 | 325250 | 4823564 | 11 | 2026-07-01 | 2026-07-01 | 2029-04-02 | 2030-06-13 | 2030-06-13 | 2032-09-14
20223 | 5 - Hampton Roads | VDOT | 58 | US 58 | IS 95 | Urban Principal Arterial - Other Freeways or Expressways | T26730 | Bridge Replacement | No | 37254088 | 4593388 | 1054803 | 31605897 | 1 | 2022-10-01 | 2026-01-31 | 2024-08-30 | 2026-01-31 | 2026-01-31 | 2028-09-01
19244 | 6 - Fredericksburg | VDOT | 658 | MONROE BAY CIRCLE | MONROE CREEK | Rural Major Collector | T26715 | Culvert Replacement | No | 2723936.84 | 327919.22 | 612871.22 | 1783146.4 | 1 | 2027-01-15 | 2027-01-15 | 2027-04-15 | 2028-04-14 | 2028-06-14 | 2028-12-15
10584 | 6 - Fredericksburg | VDOT | 14 | THE TRAIL | GARNETT'S CREEK | Rural Minor Arterial | T26717 | Culvert Rehabilitation | No | 1138204.23 | 14208.59 | 0 | 1123995.64 | 2 | 2026-07-01 | 2026-08-01 | 2026-08-02 | 2026-08-02 | 2026-08-02 | 2027-02-02
10608 | 6 - Fredericksburg | VDOT | 614 | ROCK SPRING ROAD | EXOL SWAMP | Rural Local | T26716 | Bridge Replacement | Yes | 4634357.64 | 853040.23 | 130418.33 | 3650899.08 | 3 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2027-07-01 | 2026-07-01 | 2027-12-15
18062 | 6 - Fredericksburg | VDOT | 1 | ROUTE 0001 | RAPPAHANNOCK RIVER @ | Urban Other Principal Arterial | T26713 | Bridge Rehabilitation | No | 51211333 | 3934539 | 4658319 | 42618475 | 4 | 2027-07-01 | 2028-12-31 | 2028-01-05 | 2030-01-05 | 2030-01-06 | 2033-01-06 | Bridge is jointly owned by VDOT and locality (mostly owned by VDOT) - This is the VDOT SGR TUPC 'NEW UPC T26714 created for locality portion of project (reduce funding on T26713) Total Estimate $60,177,919 UPC T26714 SGR-locality funding to cover 14.9%+/- (locality portion) of project cost estimate UPC T26713 to cover 85.1%+/- of funding for VDOT-owned portion
27907 | 7 - Culpeper | VDOT | 1083 | Somerset Drive | Stream | Rural Local | T26640 | Culvert Replacement | Yes | 4532891 | 794725 | 598872 | 3139294 | 1 | 2026-07-21 | 2026-07-21 | 2028-09-12 | 2029-06-12 | 2029-06-12 | 2030-05-29
2029 | 8 - Staunton | VDOT | 624 | MT TORREY RD | BACK CREEK | Urban Minor Arterial | T26768 | Bridge Replacement | No | 18512668 | 2263536 | 590892 | 15658240 | 1 | 2022-10-01 | 2025-11-01 | 2025-11-01 | 2026-11-01 | 2026-11-01 | 2028-11-01 | Updated by District 5/18/2022
1031 | 8 - Staunton | VDOT | 159 | DUNLAP CREEK ROAD | DUNLAP CREEK | Rural Major Collector | T26766 | Bridge Replacement | No | 9811403 | 1055162 | 608619 | 8147622 | 2 | 2022-11-01 | 2022-11-01 | 2026-11-01 | 2027-11-01 | 2027-11-01 | 2028-11-01 | Updated by District 5/18/2022
2428 | 8 - Staunton | VDOT | 39 | MOUNTAIN VALLEY RD | GUYS RUN | Rural Minor Arterial | T26769 | Bridge Replacement | No | 13342200 | 1312116 | 603270 | 11426814 | 3 | 2023-10-01 | 2026-09-16 | 2026-09-16 | 2027-09-16 | 2027-09-16 | 2028-11-15 | Updated by District 5/18/2022
17254 | 8 - Staunton | VDOT | 707 | RED BANKS RD | N FORK SHENANDOAH RIVER | Rural Local | T26772 | Bridge Replacement | Yes | 7895002 | 443487 | 153349 | 7298166 | 4 | 2022-10-31 | 2022-10-31 | 2025-02-12 | 2025-11-10 | 2025-11-10 | 2026-10-27 | Updated by District 5/18/2022
14234 | 9 - NOVA | VDOT | 95 | INTERSTATE RT.95SB | NEABSCO CREEK | Rural Principal Arterial - Interstate | T26816 | Bridge Replacement | No | 47079151 | 3911074 | 173855 | 42994222 | 1 | 2023-01-01 | 2025-07-01 | 2024-07-01 | 2025-07-01 | 2025-07-01 | 2028-07-01 | - Absolute must
5 | 9 - NOVA | VDOT | 0 | 34TH ST(ABINGDON) | 395 & RMP D&F | Urban Local | T26814 | Bridge Rehabilitation - Substructure Rehabilitation | Yes | 9550000 | 0 | 0 | 9550000 | 2 | 2021-01-23 | 2021-01-23 | 2021-07-24 | 2023-01-10 | 2026-07-01 | 2027-06-08 | - District really needs to be programmed if at all possible, PE charges will be to UPC 118397
11375 | 9 - NOVA | VDOT | 792 | THOMAS AVENUE | SUGARLAND RUN | Rural Local | T26815 | Bridge Replacement | Yes | 6741856.95 | 1425559 | 570341.95 | 4745956 | 3 | 2026-07-01 | 2028-07-01 | 2028-07-01 | 2029-07-01 | 2029-07-01 | 2031-07-01

## IID-Local SGR Bridge Projects
Locality-Owned SGR Bridge Project Selection
Final Draft Update to FY23-FY28 SYIP
Based on July 1, 2021 BrM data
Issued: 5/23/2022
| Federal ID | Route No. | Facility Carried | Feature Intersected | Condition | Structure Name | District | NHS | Functional Class | NBI | Owner | UPC | UPC (Temp) | SGR (Local) Funding | BF (IIJA) Funding | Local Project Contributions | Other Funding | Total Funding | Project Cost Estimate | Deficit Balanced if 0 | Notes
| 20001 | 0 | Piedmont Avenue | Beaver Creek | Poor | Piedmont Bridge | 1-Bristol | Non-NHS | Urban Minor Arterial | NBI | 102-Bristol | 121136 | T26472 | 55174695.7894 | 43934924.2106 | 0 | 0 | 99109620 | 99109620 | 0 | Piedmont is now funded at a more reasonable level
| 22525 | 111 | Route 111 | Walnut Branch | Poor |  | 2-Salem | ??? | Urban Minor Arterial | NBI | ??? | 121020 | T26517 | 4217606 | 0 | 0 | 0 | 4217606 | 4217606 | 0
| 20600 | 6012 | Bedford Avenue | NS Railway | Poor |  | 3-Lynchburg | Non-NHS | Urban Minor Arterial | NBI | 118-Lynchburg | 121053 | T26458 | 14714538.7932 | 0.20679 | 0 | 0 | 14714539 | 14714539 | 0 | Now fully funded by SGR, in draft is was funded with SGR / BF (IIJA) funds
| 21583/ 21584 | 360 | 14TH Street | James River SB & NB | Poor/Poor | Mayo Bridge | 4-Richmond | NHS | Urban Other Principal Arterial | NBI | 127-Richmond | 104888 | T26472 | 48078403.9832 | 24871596.0168 | 5000000 | 12050000 | 90000000 | 90000000 | 0 | - Proposed $5M CVTA Funds shown as a Local Project Contribution - Appropriations bill for $5M earmark Community Project Grant included (links below) - https://www.congress.gov/bill/117th-congress/house-bill/2471 - https://docs.house.gov/billsthisweek/20220307/BILLS-117RCP35-JES-DIVISION-L.pdf
| 20249 | 1 | Jeff. Davis Bypass | OLD RAPPAHANNOCK CANAL | Poor |  | 6-Fredericksburg | NHS | Urban Other Principal Arterial | NBI | 111-Fredericksburg | -26712 | T26712 | 6008244.551 | 9635775 | 0 | 0 | 15644019.551 | 15644020 | -0.44905
| 105 | 0 | ARLINGTON RIDGE RD | FOUR MILE RUN | Poor |  | 9-NOVA | Non-NHS | Urban Minor Arterial | NBI | 0-Arlington | 118306 | T23728 | 6736388.9146 | 6346343.0854 | 5000000 | 8308090 | 26390822 | 26390822 | 0
[12 empty] | TOTAL |  | 134929878.0314 | 84788638.5195 | 10000000 | 20358090 | 250076606.551 | 250076607 | -0.44905